PORTFOLIO WORK SAMPLE

# RFP & Procurement Analysis

Queensboro Transit Authority - Multi-Site Custodial & Facility Support Services

| Prepared by | Michael Ngo |
| --- | --- |
| Source | Fictional RFP No. QTA-26-117 |
| Purpose | Demonstrate solicitation analysis, bid strategy, risk review, and response planning |
| Recommendation | CONDITIONAL PURSUE |
| Overall Risk | Moderate-High |
| Decision Window | Complete operational validation before September 29, 2026 |

FICTIONAL CASE STUDY - NO REAL AGENCY, CLIENT, PRICING, OR EMPLOYER DATA.

# Executive Decision Brief

RECOMMENDATION - CONDITIONAL PURSUE The opportunity is strategically attractive and aligns with a scaled custodial-services provider, but pursuit should proceed only if Operations validates a credible 24/7 staffing model, the company confirms bonding capacity, and a licensed/qualified partner strategy closes specialty and participation gaps.

| Decision Factor | Assessment | Why It Matters |
| --- | --- | --- |
| Strategic fit | Strong | Large, visible, multi-year public-sector contract aligned with core custodial capabilities. |
| Operational fit | Moderate | 625,000 SF across 20 sites is manageable, but station coverage and 24/7 critical operations increase complexity. |
| Commercial fit | Moderate | Five-year potential is attractive; wage escalation cap, deductions, and price realism require disciplined costing. |
| Compliance fit | Moderate | Bonding, prevailing wage, MWBE/SDVOB goals, mandatory visits, and security clearance require early action. |
| Competitive position | Potentially strong | Quality controls and bid-management systems can differentiate if supported by credible transit/public-facing experience. |
| Overall | CONDITIONAL PURSUE | Proceed to site visits and pricing only after completing the gating actions below. |

# Immediate Gating Actions

| Owner | Action | Deadline | Go / No-Go Test |
| --- | --- | --- | --- |
| Operations | Validate staffing by facility, shift, relief pool, travel, and supervisor coverage | Sep 17 | No unresolved critical post or unrealistic productive-hour assumption |
| Finance / Surety | Confirm 5% bid security and 100% performance/payment bonding | Sep 17 | Written indication within expected contract range |
| HR / Security | Validate recruiting and clearance timeline for control-center staff | Sep 18 | Cleared pipeline can be ready before go-live |
| Procurement | Register and schedule all three mandatory site-visit clusters | Immediate | Attendance confirmed for each cluster |
| Supplier Diversity | Identify credible MWBE and SDVOB work packages | Sep 22 | Plan reaches goals or has defensible good-faith strategy |
| Pricing | Model prevailing wage, supplements, relief, deductions, equipment, and escalation | Oct 2 | Price is sustainable under downside scenarios |

# 1. Opportunity Summary

| Item | Analysis |
| --- | --- |
| Client / Procurement | Queensboro Transit Authority; best-value RFP QTA-26-117 |
| Scope | Comprehensive custodial and facility support across 20 locations / approx. 625,000 SF |
| Term | Three-year base plus two one-year options |
| Submission | Electronic portal; five separate volumes; pricing workbook separate |
| Award Model | Single award; all locations required; partial bid prohibited |
| Critical Dates | Mandatory visits Sep 21-23; questions Sep 29; proposals Oct 22; start Feb 1 |
| Commercial Model | Firm-fixed annual location pricing plus unit rates; limited escalation |
| Key Differentiator | Credible operations and transition plan supported by auditable quality/workflow controls |

## Opportunity Narrative

QTA is not merely buying cleaning labor. It is seeking reliable facility continuity across three distinct operating environments: conventional administrative space, industrial/maintenance support, and high-traffic public transit locations. The bid should therefore be treated as an operational-services procurement in which staffing reliability, security, rapid response, and quality governance are as important as price.

The opportunity is designed to reward a proposer that can translate a complex site portfolio into a controlled management system. That favors a response built around facility segmentation, shift-level coverage, relief planning, mobile inspections, root-cause correction, and a disciplined transition command structure.

# 2. Scope Interpretation

## 2.1 Service Environments

| Environment | Operational Reality | Proposal Implication |
| --- | --- | --- |
| Administrative | Predictable occupancy; executive and hearing spaces | Emphasize appearance, discretion, schedule coordination, and periodic care |
| 24/7 critical operations | No lapse in coverage; cleared staff only | Dedicated cleared bench, shift handoffs, redundancy, emergency escalation |
| Customer-facing center | High-touch, variable public demand | Day porter responsiveness, consumables monitoring, complaint closure |
| Maintenance support | Industrial soils and vehicle activity | Define custodial boundary, safety training, equipment selection, exclusions |
| Passenger stations | Open while cleaning; weather and incident exposure | Continuous porter model, passenger-safe work zones, mobile response |

## 2.2 Included, Ambiguous, and Excluded Work

| Classification | Examples | Action |
| --- | --- | --- |
| Clearly included | Routine custodial, floor care, interior/access-height glass, waste, day porter, periodic services | Price and staff directly |
| Included but quantity-sensitive | Passenger incidents, emergency response, pressure washing, carpet extraction, exterior glass | Validate historical volume and price unit-rate exposure |
| Ambiguous | Industrial soil boundary; added/removed locations; inventory loss; above-ground glass; event surges | Submit targeted questions and define assumptions |
| Generally excluded | Hazardous-material remediation, regulated biohazard disposal, major water restoration | State exclusion unless separately authorized |

# 3. Requirements and Compliance Matrix

| ID | Requirement | Status | Response Location / Action |
| --- | --- | --- | --- |
| R-01 | Attend all three mandatory site-visit clusters | Open | Procurement to register; retain sign-in proof |
| R-02 | Price all base locations and years | Open | Cost model and separate price workbook |
| R-03 | Provide 5% bid security | Open | Surety confirmation before proposal development |
| R-04 | Commit to 100% performance and payment bonds | Open | Finance and surety letter |
| R-05 | Meet prevailing wage and supplements | Open | Validate addendum schedule and costing basis |
| R-06 | Provide dedicated contract manager and required supervision | Open | Org chart, resumes, staffing narrative |
| R-07 | Maintain 12% relief capacity | Open | Relief roster and financial model |
| R-08 | Security clear critical staff before start | Open | Recruiting and screening plan |
| R-09 | 20% MWBE and 6% SDVOB goals / good-faith effort | Open | Subcontracting plan and outreach log |
| R-10 | Self-perform core management and 70% routine hours | Review | Check participation allocations |
| R-11 | Meet insurance incl. $10M excess / $2M cyber | Open | Broker review |
| R-12 | Submit searchable PDFs within page limits | Planned | Compliance outline and production checklist |
| R-13 | Acknowledge all addenda | Open | Final submission control |
| R-14 | Disclose all exceptions in Form H | Open | Legal/commercial review |

# 4. Procurement Schedule and Workback Plan

| Phase | Dates | Primary Outputs |
| --- | --- | --- |
| Qualification and gate review | Sep 8-17 | Opportunity brief, bonding check, initial staffing model, pursue decision |
| Field intelligence | Sep 18-23 | Pre-proposal conference, three site visits, counts/conditions, operational notes |
| Clarification | Sep 24-29 | Consolidated questions; assumption register |
| Solution and costing | Sep 24-Oct 6 | Staffing plan, productivity model, equipment, partner allocations, price scenarios |
| Draft development | Oct 1-12 | Technical, team, transition, quality, participation, and price narratives |
| Review and validation | Oct 13-18 | Red review, cost reconciliation, compliance audit, reference checks |
| Final production | Oct 19-21 | Gold review, signatures, bid security, addenda, file QA, portal staging |
| Submission | Oct 22 before 12 PM internal target | Portal upload, receipt, archive |

# 5. Risk Register

| Risk | Likelihood | Impact | Mitigation / Decision Rule |
| --- | --- | --- | --- |
| Unrealistic station productive-hour model | Medium | High | Observe passenger flow and service windows; build bottom-up posts; reject arbitrary SF-only productivity. |
| Control-center clearance delay | Medium | Critical | Pre-screen dedicated candidates; maintain cleared relief; make HR plan a pursuit gate. |
| Prevailing-wage underpricing | Medium | Critical | Use correct classification, supplements, escalation scenarios, and payroll burden; reconcile every year. |
| Escalation cap below labor growth | Medium | High | Model statutory adjustment treatment and residual exposure; clarify change mechanism. |
| Service deductions erode margin | Medium | High | Price relief and QA; model downside deduction scenario; assign corrective-action governance. |
| MWBE / SDVOB goal infeasibility | Medium | Medium | Package periodic services/equipment/logistics; begin documented outreach early. |
| Incumbent transition disruption | Medium | High | Create outreach and onboarding schedule; maintain independent recruiting pipeline. |
| Scope creep at maintenance sites | High | Medium | Define industrial soil and hazardous response boundary; require authorization for excluded work. |
| Added/removed facilities pricing dispute | Medium | Medium | Seek unit-price and staffing adjustment methodology in Q&A. |
| Portal / administrative failure | Low | Critical | Stage files one day early; internal noon deadline; independent compliance check. |

## Risk Heat Summary

PRIMARY RISK CONCENTRATION The most material risks are operational rather than rhetorical: security-cleared labor, 24/7 post coverage, prevailing-wage cost accuracy, escalation protection, and defensible staffing at open passenger facilities.

# 6. Commercial and Pricing Considerations

## 6.1 Cost Model Structure

Direct productive labor by location, role, shift, day type, and service frequency.

Nonproductive coverage: breaks, travel, shift handoff, training, meetings, and security processing.

Relief capacity at or above 12% of scheduled hours.

Prevailing-wage base, supplements, payroll taxes, workers compensation, and statutory changes.

Dedicated management, quality/safety, recruiting, and administrative support.

Equipment capitalization/replacement, chemicals, liners, PPE, vehicles, technology, and storage constraints.

Periodic services and specialty partner costs.

Bonding, insurance, overhead, contingency, profit, and expected performance-deduction exposure.

## 6.2 Pricing Traps

| Trap | Why It Is Dangerous | Control |
| --- | --- | --- |
| Using blended SF productivity across all sites | Public stations and 24/7 control space are post-driven, not simple task-frequency environments | Separate post-based and task-based labor models |
| Ignoring relief in base hours | Contract explicitly requires 12% relief and critical vacancies create deductions | Show relief as funded labor, not assumed overtime |
| Applying 3% escalation mechanically | Statutory wage changes may differ; contract language must be interpreted | Model base, downside, and statutory-adjustment scenarios |
| Treating emergency unit rates as upside only | Response obligation creates readiness cost even without calls | Fund on-call supervision and dispatch readiness |
| Underfunding QA | Inspection scores and recurrence directly affect deductions and reputation | Price independent QA and corrective-action time |

## 6.3 Scenario Analysis Required

| Scenario | Purpose |
| --- | --- |
| Base case | Expected staffing, full performance, normal absenteeism |
| Labor stress | Wage/supplement increases exceed ordinary escalation |
| Coverage stress | Absence rate and overtime above plan during winter / hiring gap |
| Performance stress | Illustrative monthly deductions and rework |
| Mobilization stress | Clearance delays, equipment expediting, overlapping transition labor |
| Scope adjustment | One station cluster added or removed |

# 7. Operational Questions for QTA

| Topic | Proposed Question |
| --- | --- |
| Facility data | Please provide restroom fixture counts, floor-type quantities, carpet and resilient-floor areas, consumable usage, and historical service hours by location. |
| Station coverage | Please confirm required continuous porter posts and hours for each station, including whether specified posts are minimum staffing or performance expectations. |
| Incumbent information | Please provide current staffing hours, wage classifications, union status if applicable, and available incumbent transition data. |
| Security clearance | What is the average clearance timeline, who bears related costs, and may candidates begin screening before contract execution? |
| Incident volume | Please provide the prior 12 months of emergency calls, passenger-incident cleanups, weather responses, and special-event requests. |
| Industrial boundary | Please clarify the distinction between routine custodial cleaning and excluded industrial/hazardous remediation at maintenance facilities. |
| Escalation | Please confirm that documented statutory prevailing-wage and supplement changes are handled outside the ordinary escalation cap. |
| Facility changes | What pricing and staffing method will apply when locations or square footage are added, removed, or materially repurposed? |
| Deductions | Are deductions subject to a monthly cap, cure period, root-cause review, and exclusion for QTA-caused access or supply failures? |
| Technology | Does QTA require a particular platform, integration, data-hosting location, or API/export format? |
| Participation | Which categories of spend count toward MWBE/SDVOB goals, and may certified suppliers and equipment lessors count? |
| Pricing | Will QTA provide a required productive-labor-hour schedule or evaluate proposer-designed staffing solely for realism? |

## Question Prioritization

IF QUESTIONS ARE LIMITED Prioritize station post requirements, wage/escalation treatment, incumbent staffing, clearance timing, and facility-change pricing. Each can materially change the labor model or pursuit decision.

# 8. Proposal Strategy

## 8.1 Recommended Win Theme

CORE MESSAGE Reliable service at every operating environment - supported by site-specific staffing, cleared relief capacity, transparent quality data, and a controlled 45-day transition.

## 8.2 Supporting Themes

| Theme | Proof / Content Needed |
| --- | --- |
| Continuity without improvisation | Shift-level coverage, 12% relief pool, recruiting funnel, clearance milestones, escalation tree |
| One portfolio, tailored operating models | Separate plans for offices, control center, maintenance sites, customer center, and stations |
| Quality data that drives correction | Inspection cadence, issue aging, repeat-deficiency analysis, monthly executive reporting |
| Safe work in live transit environments | Passenger controls, chemical/equipment selection, incident protocols, safety observations |
| Transition readiness | Day-by-day mobilization plan, command structure, risk log, go-live rehearsal |
| Responsible best-value pricing | Transparent staffing assumptions, funded supervision/relief, realistic periodic work |

## 8.3 Likely Competitive Weaknesses to Avoid

Generic corporate narrative not tied to QTA’s five operating environments.

A single square-foot productivity rate with no post or shift logic.

Heavy reliance on uncommitted subcontractors to meet core coverage.

Claims of “zero disruption” without a clearance and relief plan.

Technology screenshots without showing who acts on the data.

Low price created by omitting supervision, relief, periodic work, or wage supplements.

# 9. Response Architecture

| Volume / Section | Purpose | Owner Inputs |
| --- | --- | --- |
| Executive letter | Frame value, commitment, and conditional assumptions | Executive sponsor; bid lead |
| Understanding and approach | Show operating-environment insight and service methodology | Operations; safety; quality |
| Staffing and management | Shift model, relief, org chart, escalation, recruiting | Operations; HR; pricing |
| Mobilization | 45-day workplan, clearance, equipment, transition control | Project manager; HR; IT |
| Quality / safety / technology | Inspection, issue closure, reporting, training, passenger safety | Quality; safety; IT |
| Experience and team | Relevant scaled/public-facing contracts and key resumes | Proposal lead; references |
| Participation | Work packages, partners, outreach, self-performance compliance | Supplier diversity; procurement |
| Price narrative | Assumptions, cost integrity, escalation, units, exceptions | Pricing; finance; legal |

# 10. Responsibility Matrix

| Workstream | Accountable | Responsible / Consulted | Deliverable |
| --- | --- | --- | --- |
| Pursuit decision | Executive sponsor | Bid lead, Operations, Finance | Documented go/no-go approval |
| Compliance | Bid lead | Legal, Finance, Admin | Compliance matrix and final audit |
| Site intelligence | Operations lead | Supervisors, Bid lead | Visit reports, counts, staffing assumptions |
| Staffing solution | Operations lead | HR, Pricing, Safety | Shift/post plan and relief model |
| Costing | Pricing lead | Operations, Finance, Partners | Reconciled cost model and price forms |
| Technical narrative | Bid lead | Operations, SMEs | Volumes 2-3 |
| Participation | Procurement / diversity lead | Bid lead, Partners | Volume 4 and outreach evidence |
| Final production | Bid lead | Admin, Executive signer | Approved files and portal receipt |

# 11. Bid / No-Bid Scorecard

| Criterion | Weight | Score (1-5) | Weighted | Rationale |
| --- | --- | --- | --- | --- |
| Service alignment | 15 | 5 | 15.0 | Core custodial scope with adjacent periodic work |
| Geographic fit | 10 | 5 | 10.0 | Concentrated within operating region |
| Contract value / term | 10 | 5 | 10.0 | Large multi-year revenue potential |
| Operational feasibility | 20 | 3 | 12.0 | 24/7, stations, relief, and clearance require validation |
| Competitive position | 10 | 3 | 6.0 | Potentially credible; transit-specific proof may be limited |
| Compliance / bonding | 15 | 3 | 9.0 | Material but potentially manageable gates |
| Commercial risk | 15 | 3 | 9.0 | Escalation cap and deductions require careful modeling |
| Proposal capacity | 5 | 4 | 4.0 | Six-week schedule supports structured response |
| TOTAL | 100 |  | 75.0 / 100 | Conditional pursue threshold: 70, with no failed mandatory gate |

## Decision Conditions

Confirm bonding and insurance feasibility before incurring significant proposal expense.

Complete bottom-up staffing validation after mandatory site visits.

Confirm security-clearance recruiting path and relief capacity.

Resolve or price the wage-escalation and facility-change mechanisms.

Establish credible participation partners without violating the 70% self-performance requirement.

# 12. Final Recommendation

CONDITIONAL PURSUE Advance the opportunity through mandatory site visits, Q&A, and preliminary costing. Convert to an unconditional pursue only when the five decision conditions above are satisfied. If any critical gate fails - particularly bonding, clearance readiness, or a sustainable staffing model - recommend no-bid despite the strategic attractiveness.

This recommendation reflects disciplined selectivity rather than risk avoidance. The opportunity deserves investment because it aligns with core capabilities and provides meaningful long-term value. However, the proposal should not rely on narrative strength to cover unresolved operational or commercial assumptions. The strongest response will be the one whose staffing, pricing, transition, and performance model tell the same coherent story.

# Appendix A - Submission Readiness Checklist

☐ All mandatory visits attended and documented

☐ All addenda received and acknowledged

☐ Bid security correct and executed

☐ All locations and years priced

☐ Cost model reconciles to forms

☐ Prevailing-wage schedule validated

☐ Bonds and insurance confirmed

☐ Key personnel resumes approved

☐ References contacted and available

☐ Partners identified and certifications verified

☐ Participation math reconciles with self-performance

☐ Exceptions disclosed in Form H

☐ Page limits and file names verified

☐ Searchable PDFs pass quality check

☐ Signatures and notarizations complete

☐ Portal upload completed before internal deadline

☐ Receipt saved to opportunity record

# Appendix B - Analytical Methods Demonstrated

Executive opportunity briefing

Requirements decomposition and compliance traceability

Scope segmentation and ambiguity analysis

Operational and commercial risk assessment

Question development and prioritization

Pricing-driver identification and scenario planning

Proposal strategy and win-theme development

Workback scheduling and responsibility assignment

Weighted bid/no-bid scoring

Conditional recommendation with explicit decision gates

PORTFOLIO STATEMENT This analysis was prepared by Michael Ngo as a fictional professional work sample. It demonstrates methodology and judgment; it does not represent advice to, analysis for, or confidential information from any real organization.