ADDENDUM NO. 1

# Multi-Site Custodial & Facility Support Services

Solicitation amendments and responses to proposer questions

| Issuing Entity | Queensboro Transit Authority (QTA) |
| --- | --- |
| Solicitation | RFP No. QTA-26-117 |
| Addendum Issued | October 6, 2026 |
| Original Due Date | October 22, 2026 at 2:00 PM ET |
| Revised Due Date | October 27, 2026 at 2:00 PM ET |
| Questions Addressed | 24 proposer questions |

THIS ADDENDUM AND THE UNDERLYING PROCUREMENT ARE ENTIRELY FICTIONAL.

# Addendum Notice

This Addendum No. 1 forms part of RFP No. QTA-26-117. Proposers must acknowledge receipt in Form B. Except as expressly modified below, all solicitation requirements remain unchanged. If this Addendum conflicts with the original RFP, this Addendum governs.

IMPORTANT PROPOSAL IMPACT The proposal deadline is extended by five calendar days. QTA has also clarified wage escalation, control-center clearances, minimum station posts, monthly deduction limits, pricing for facility changes, and revised square footage. Proposers should update staffing, price, compliance, and risk assumptions accordingly.

# 1. Summary of Formal Amendments

| Amendment | RFP Reference | Change |
| --- | --- | --- |
| A-01 | Procurement Schedule | Proposal deadline changes from October 22 to October 27, 2026 at 2:00 PM ET. Internal portal file limits remain unchanged. |
| A-02 | Section 3 - Facility Portfolio | Station Cluster B increases from approximately 111,000 SF to 117,500 SF. Total portfolio increases from approximately 625,000 SF to 631,500 SF. |
| A-03 | Section 5.1 - Minimum Coverage | Adds minimum station porter posts by cluster and clarifies that proposers may recommend supplemental coverage. |
| A-04 | Section 5.2 - Workforce | Prevailing-wage schedule QTA-PW-2026-44 is incorporated as Attachment 1. Documented statutory wage/supplement changes are outside the ordinary 3% escalation cap. |
| A-05 | Section 5.3 - Mobilization | QTA may begin clearance processing after notice of intent to award and before final contract execution, at proposer risk. |
| A-06 | Section 6.3 - Deductions | Aggregate routine service deductions are capped at 8% of the monthly invoice, excluding fraud, willful misconduct, abandonment, indemnity, and separately recoverable damages. |
| A-07 | Section 7 - Bonds | Performance and payment bonds are reduced from 100% to 50% of the first-year contract value. Bid security remains 5%. |
| A-08 | Section 10 - Pricing | Adds a required facility-change pricing formula based on approved staffing hours plus documented non-labor impacts. |

# 2. Revised Procurement Schedule

| Milestone | Revised Date / Status |
| --- | --- |
| RFP issued | September 8, 2026 |
| Pre-proposal conference | Completed September 18, 2026 |
| Mandatory site visits | Completed September 21-23, 2026 |
| Questions due | Completed September 29, 2026 |
| Addendum No. 1 | October 6, 2026 |
| Proposal due - REVISED | October 27, 2026 at 2:00 PM ET |
| Interviews / presentations | Week of November 16, 2026, if requested |
| Notice of intent to award | December 11, 2026 |
| Service commencement | February 1, 2027 |

# 3. Revised Minimum Station Coverage

The following posts are minimum continuous coverage during the stated windows. Proposers remain responsible for proposing sufficient additional task labor, supervision, relief, periodic-service labor, and emergency capacity to meet all performance requirements.

| Cluster | Minimum Posts | Coverage Window | Clarification |
| --- | --- | --- | --- |
| Station Cluster A | 4 porter posts | 5:00 AM-1:00 AM daily | One post may rotate between two adjacent low-volume stations only with QTA approval. |
| Station Cluster B | 6 porter posts | 5:00 AM-1:00 AM daily | Includes one dedicated public-restroom post during 7:00 AM-10:00 PM. |
| Station Cluster C | 3 porter posts | 5:00 AM-1:00 AM daily | Weekend reduction to two posts may be proposed with supporting passenger-volume analysis. |
| All clusters | 1 floating supervisor per active shift | Overlapping first and second shifts | Supervisor may cover multiple clusters but may not replace a required porter post except during an emergency. |

PRICING INSTRUCTION Minimum posts are not a complete staffing prescription. Price realism will consider whether the proposer separately funds breaks, relief, task work, supervision, periodic services, travel, training, and absence coverage.

# 4. Revised Facility Data

| Facility / Cluster | Original SF | Revised SF | Reason |
| --- | --- | --- | --- |
| Station Cluster B | 111,000 | 117,500 | Added mezzanine, staff rooms, and revised platform-area estimate |
| Total Portfolio | 625,000 | 631,500 | Net increase of 6,500 SF |

Attachment 2 includes revised floor-type estimates for Station Cluster B. All quantities remain planning estimates and are subject to field verification during mobilization.

# 5. Responses to Proposer Questions

Question 1 - Section 3 - Facility Data

Q: Will QTA provide restroom fixture counts, floor-type quantities, carpet areas, and resilient-floor quantities by location?

A: Yes. Attachment 2 provides planning quantities. Proposers must use the revised Station Cluster B square footage. Minor field variances will not automatically change price; material scope changes will use the facility-change process.

Question 2 - Section 5.1 - Station Coverage

Q: Are station porter posts minimum staffing requirements or performance expectations?

A: The posts listed in Section 3 of this Addendum are minimum continuous posts. They do not replace the proposer’s obligation to calculate task labor, periodic work, relief, supervision, and emergency capacity.

Question 3 - Section 5.1 - Productive Hours

Q: Will QTA provide the incumbent’s total productive labor hours?

A: QTA will provide aggregated scheduled hours in Attachment 3 for informational purposes only. QTA does not warrant that incumbent staffing is sufficient, efficient, or appropriate for the new contract.

Question 4 - Section 5.2 - Incumbent Workforce

Q: Is the current workforce unionized, and must the successful proposer retain incumbent employees?

A: Certain incumbent employees are represented under a collective bargaining agreement. QTA does not direct hiring decisions. The successful proposer must comply with applicable law and submit an incumbent-outreach plan. Proposers are responsible for their own labor and legal review.

Question 5 - Section 5.2 - Prevailing Wage

Q: Will statutory prevailing-wage and supplement increases be limited by the 3% annual escalation cap?

A: No. Verified statutory changes to required wage rates or supplements will be addressed through an equitable price adjustment. The ordinary cap applies to other annual escalation.

Question 6 - Section 5.3 - Security Clearance

Q: What is the typical clearance timeline for Operations Control Center personnel?

A: QTA’s current planning estimate is four to six weeks after receipt of a complete candidate package. QTA will prioritize initial candidates but does not guarantee completion dates. The contractor must maintain recruitment redundancy.

Question 7 - Section 5.3 - Security Clearance

Q: May the apparent successful proposer begin screening before the contract is executed?

A: Yes. After notice of intent to award, QTA may accept candidate packages before execution. Any recruiting or screening cost incurred before contract execution remains at the proposer’s risk.

Question 8 - Section 4.3 - Emergency Services

Q: How many emergency or incident responses occurred during the previous year?

A: For planning purposes, QTA recorded 146 passenger-incident cleanups, 19 weather-response activations, 8 minor water-intrusion events, and 11 special-event surges across the portfolio. These figures are historical and are not guaranteed volumes.

Question 9 - Section 4.3 - Emergency Services

Q: Does the 90-minute response requirement apply when an on-site porter can make the area safe?

A: An on-site employee may perform immediate isolation and basic response when trained and equipped. The 90-minute requirement applies when additional personnel, specialized equipment, or supervisory response is requested.

Question 10 - Section 4.1 - Maintenance Facilities

Q: Please clarify the boundary between custodial cleaning and industrial or hazardous remediation.

A: Routine dust, tracked soil, non-hazardous grease spotting, locker rooms, offices, and ordinary floor cleaning are included. Chemical spills, regulated waste, petroleum releases, asbestos, lead disturbance, and other hazardous remediation are excluded unless separately authorized to a qualified provider.

Question 11 - Section 4.4 - Consumables

Q: What were QTA’s prior-year paper, soap, and sanitizer usage levels?

A: Attachment 4 provides annual planning quantities. QTA purchases the products; the contractor receives, stores, distributes, replenishes, and reports inventory. Normal usage is not charged to the contractor.

Question 12 - Section 4.4 - Inventory Loss

Q: How will unexplained product loss be determined?

A: QTA will compare receipts, documented issues, reasonable on-hand inventory, and service demand. No chargeback will be assessed without notice, supporting documentation, and an opportunity for the contractor to respond.

Question 13 - Section 6.3 - Service Deductions

Q: Are monthly service deductions capped?

A: Routine service deductions are capped at 8% of the applicable monthly invoice. The cap does not limit recovery for fraud, willful misconduct, abandonment, indemnity obligations, property damage, or separately documented replacement costs.

Question 14 - Section 6.3 - Cure Process

Q: Will the contractor have an opportunity to dispute deficiencies?

A: Yes. Critical conditions must be addressed immediately. For invoice deductions, QTA will issue supporting documentation and allow five business days for a written response before final assessment.

Question 15 - Section 10 - Facility Changes

Q: How will pricing be adjusted if locations are added or removed?

A: The adjustment will begin with approved staffing hours multiplied by the applicable fully burdened labor rate, plus or minus documented supervision, equipment, supply, travel, and subcontractor impacts. Overhead and profit percentages may not exceed those in the original proposal.

Question 16 - Section 7 - Participation Goals

Q: Can certified suppliers and equipment lessors count toward MWBE or SDVOB participation?

A: Only the commercially useful function and eligible portion of spend will count. Proposers should distinguish suppliers, brokers, lessors, and service subcontractors and provide certification documentation.

Question 17 - Section 7 - Self-Performance

Q: Does subcontracted periodic floor care count against the requirement that the prime self-perform 70% of routine labor hours?

A: Periodic specialty projects are excluded from the denominator. The 70% requirement applies to routine scheduled custodial and porter labor hours.

Question 18 - Section 7 - Cyber Liability

Q: Why is cyber liability insurance required for a custodial contract?

A: The contractor will access QTA’s workforce, inspection, issue-management, and facility systems. The $2 million requirement remains unchanged.

Question 19 - Section 7 - Bonds

Q: Will QTA reduce the performance and payment bond amounts?

A: Yes. Each bond is revised to 50% of the first-year contract value. Bid security remains 5% of the total evaluated first-year price.

Question 20 - Section 8 - Page Limits

Q: Do resumes, organization charts, and required forms count toward technical page limits?

A: Required forms, divider pages, the table of contents, and resumes in Volume 3 do not count. Organization charts and substantive graphics within Volume 2 do count.

Question 21 - Section 8 - Submission

Q: May pricing PDFs be password protected?

A: No. Pricing must be submitted as the unlocked QTA spreadsheet and a searchable PDF. Files must not require passwords, macros, external links, or proprietary viewers.

Question 22 - Section 9 - Price Realism

Q: Will QTA disclose a minimum acceptable staffing level beyond the stated posts?

A: No. QTA will evaluate whether each proposed staffing model can reasonably perform the scope. Proposers should clearly disclose posts, task hours, relief, periodic labor, and management hours.

Question 23 - Section 9 - Interviews

Q: Who must attend a requested oral presentation?

A: At minimum: the proposed Contract Manager, lead Cluster Supervisor, executive sponsor, and individual responsible for quality/performance reporting. Substitutions require QTA approval.

Question 24 - Section 10 - Pricing

Q: Should emergency hourly rates include equipment and consumables?

A: Hourly labor rates should include ordinary PPE and hand tools. The dispatch fee should include routine vehicle and mobilization cost. Extraordinary equipment or regulated disposal requires prior written authorization and supporting cost documentation.

# 6. Attachments Incorporated by Addendum

| Attachment | Description | Proposal Use |
| --- | --- | --- |
| Attachment 1 | Fictional Prevailing Wage Schedule QTA-PW-2026-44 | Cost labor classifications and supplements; do not apply ordinary escalation cap to statutory changes |
| Attachment 2 | Revised Facility and Floor-Type Planning Data | Update Cluster B quantity and periodic-work calculations |
| Attachment 3 | Incumbent Aggregate Scheduled Hours | Benchmark only; proposer remains responsible for staffing adequacy |
| Attachment 4 | Historical Consumable and Emergency-Response Data | Support logistics, porter, storage, and emergency-readiness assumptions |
| Attachment 5 | Revised Pricing Workbook Instructions | Apply facility-change methodology and revised bond assumptions |

# 7. Addendum Acknowledgment

Proposer acknowledges receipt of Addendum No. 1 and confirms that all changes have been incorporated into its technical proposal, staffing plan, pricing, exceptions, and required forms.

Proposer Legal Name: ______________________________________________________________

Authorized Representative: ______________________________________________________________

Signature: ______________________________________________________________

Title: ______________________________________________________________

Date: ______________________________________________________________

PORTFOLIO STATEMENT This fictional addendum was created to demonstrate addendum review, change control, question development, and the translation of procurement clarifications into proposal actions.